## Quaterly Goals
🎯 Overall 3-Month Goals
Operational Stability: Achieve accurate store management (stock, pricing, promotions) and routine content updates.
Deep SEO Overhaul: Complete audits, fix technical elements, and optimize content/metadata on top 100 key pages for major organic growth.
Profitable Paid Channel: Successfully set up, launch, and stabilize optimized Google Ads campaigns for B2B audiences.
Performance Clarity: Implement and utilize Looker Studio/GA dashboards for data-driven decision-making.

## Monthly Goals
Month | Core Activities / Deliverables | Story points | Goals (Summary) | Estimated Hours
Month 1 | 1. Store Management: Low/Out-of-Stock Mgmt, Price & Sale Verification (promotions, discount codes), Homepage & Collection Updates (new products). |  | 1. Store Hygiene: Standardize daily/weekly checks. | 100
| 2. SEO Audit & Content: Full website SEO audit, Content Audits (Product, Collection, Pages), B2B keyword research, Content writing/updation. |  | 2. SEO Audit & Research: Complete audits and B2B keyword research.
| 3. Optimization: Metadata writing/optimization for top 35 pages (Meta Title/Description/Keyword, H1/H2, Product description, FAQs, Images, Slug). |  | 3. Top Page Optimization: Optimize content on the top 35 pages.
| 4. Technical SEO: Fixes for 35 identified pages (site speed, mobile, security, architecture, schema, duplicate content). |  | 4. Technical Fixes - Wave 1: Resolve critical technical issues on 35 pages.
| 5. Content: Create and Publish 2 blog posts. |  | 5. Reporting Setup: Configure initial dashboards.
| 6. Reporting: Generate report (Looker Studio / GA). |  | 6. 2 blog posts.
Month 2 | 1. Store Management: Low/Out-of-Stock Mgmt, Price & Sale Verification, Homepage & Collection Updates. |  | 1. Store Hygiene: Standardize daily/weekly checks. | 100
| 2. SEO Audit & Content: Continued Content Audits, B2B keyword research, Content writing/updation. |  | 2. SEO Audit & Research: Complete audits and B2B keyword research.
| 3. Optimization: Metadata writing/optimization for top 30 pages. |  | 3. Top Page Optimization: Optimize content on the top 30 pages.
| 4. Technical SEO: Fixes for 35 identified pages. |  | 4. Technical Fixes - Wave 1: Resolve critical technical issues on 30 pages.
| 5. Content: Create and Publish 2 blog posts. |  | 5. Reporting Setup: Configure initial dashboards.
| 6. Google Ads Setup: Comprehensive audience/keyword research, Campaign structure design (Shopping, Search, B2B), Merchant Center setup, Ad copywriting, Conversion tracking setup (GA4, GTM), Landing page creation/optimization, Internal QA. |  | 6. 2 blog posts.
| 7. Reporting: Generate report (Looker Studio / GA). |  | 7. Google Ads Setup & QA: Complete full campaign structure and validate conversion tracking for launch.
Month 3 | 1. Store Management: Low/Out-of-Stock Mgmt, Price & Sale Verification, Homepage & Collection Updates. |  | 1. Final SEO Implementation: Complete content optimization for 35 final pages and finish the last 35 technical fixes. | 100
| 2. SEO Audit & Content: Continued Content Audits, B2B keyword research, Content writing/updation. |  | 2. Ads Launch & Stabilization: Successfully launch campaigns and actively track/reallocate budget.
| 3. Optimization: Metadata writing/optimization for top 35 pages. |  | 3. Performance Optimization: Initiate continuous A/B testing to improve ROAS/CPL.
| 4. Technical SEO: Fixes for 35 identified pages. |  | 4. Reporting Setup: Configure initial dashboards.
| 5. Content: Create and Publish 2 blog posts. |  | 5. 2 blog posts.
6. Google Ads Execution: Ads Launch & Watch (tracking CPC, CTR, conversion data), Budget reallocation, Continuous optimization of keywords/bids/audiences, A/B testing (ad copy/creatives/LPs), Ads Scaling & SEO Expansion.
7. Reporting: Generate report (Looker Studio / GA).

## Modules
Module 1: Shopify Store Management |  |  |  | Module 2: Google Ads
Activity/Task | Basic $1199/mothly | Pro $2499/monthly |  | Activity/Task | Basic $799/mothly | Pro $1199/monthly | Elite $1499/monthly
I. Core Operations & Inventory |  |  |  | I. Campaign Setup | 1 | 2 | 2025-02-04
Inventory Updates & Monitoring (SKUs) | 50 | 100 |  | PPC Monthly Spend (USD) | $0 – $1,000 | $1,001 – $5,000 | $5,000+
II. Product & Content Management |  |  |  | Keyword Research | ✓ | ✓ | ✓
Dedicated Shopify Store Manager Access | ✓ | ✓ |  | Ad Account Setup | ✓ | ✓ | ✓
Product Uploads, Edits, Price, Descriptions, Tagging, & Collection | 50 | 100 |  | Ad Copy Development | ✓ | ✓ | ✓
Blog Writing & Scheduling | 2 | 4 |  | Bid Setup | ✓ | ✓ | ✓
Social Media Post Creation (Image + Caption) | 6 | 10 |  | Landing Page Development (Count) | 1 | 2025-01-02 | 2025-01-03
Visuals, Banners, and Promo Graphic Creation | Standard Assets | Custom Creatives/Design |  | Conversion Tracking | ✓ | ✓ | ✓
III. Technical & Maintenance |  |  |  | II. Google Ad Optimization
Theme Updates & App Installation | ✗ | 3-5 times updates, 1-2 Apps installation |  | Text Ads | ✓ | ✓ | ✓
Minor Design Fixes & Layout Tweaks | ✗ | ✓ |  | Display Ads | ✗ | ✓ | ✓
Payment Gateway Setup & Testing | ✗ | ✓ |  | Remarketing Ad | ✗ | ✓ | ✓
IV. Advanced Strategy & Reporting |  |  |  | Content & Topic Targeting | ✗ | ✗ | ✓
Analytics Setup Overview (Shopify & GA4) | ✓ | ✓ |  | III. PPC Maintenance & Reporting
Performance Reporting & Insights | Monthly Snapshot | Bi-weekly Detailed Analysis |  | Landing Page Optimization | ✓ | ✓ | ✓
Technical Support Response Time | 24h | 8h |  | CTR Analysis | ✓ | ✓ | ✓
|  |  |  | Keyword Refinement (if Required) | ✓ | ✓ | ✓
|  |  |  | Bid Adjustment (if Required) | ✓ | ✓ | ✓
Module 3: Email Marketing |  |  |  | Ad Extensions | ✓ | ✓ | ✓
Activity/Task | Basic $99/monthly | Pro $499/monthly | Elite $999/monthly | Ad Scheduling and Geographical Marketing | ✓ | ✓ | ✓
Email Send Limit (Per Month) | 7000 | 30000 | 70000 | Campaign Performance Report | ✓ | ✓ | ✓
Email Templates | 1 | 2025-02-03 | 2025-03-05 | Conversions Improvement Suggestions | ✓ | ✓ | ✓
Responsive HTML Design | ✓ | ✓ | ✓ | A/B Testing | ✗ | ✗ | ✓
Facebook Integration | ✓ | ✓ | ✓
Unlimited Email Attachment Storage | ✓ | ✓ | ✓
Unlimited Customer Subscriptions | ✓ | ✓ | ✓
Pre-scheduled Emails | ✓ | ✓ | ✓
Transform Webpages to Emails Feature | ✓ | ✓ | ✓
Module 4: On Page SEO
Activity/Task | Basic $1499/monthly | Pro $2499/monthly | Elite $4499/monthly
I. Strategy & Scope
Keyword Focus (Keywords Optimized) | 10 | 20-30 | 20-50
Target Pages/Focus | 10 | 20 | 30
Competitive Analysis | ✗ | ✓ | ✓
II. Technical SEO
Clean up | ✓ | ✓ | ✓
Meta Titles, Description, H1 Optimization | ✓ | ✓ | ✓
Speed Optimization | ✗ | ✓ | ✓
Broken Link (404) & Redirect Management | ✓ (Audit only) | ✓ (Audit & Fixes) | ✓ (Proactive Monitoring & Fixes)
Mobile-First Indexing & Usability Review | ✗ | ✓ | ✓
Local SEO Setup | ✗ | ✗ | ✓
III. Content Optimization
Blog Writing | 2 | 4 | 6
Content Refresh/Audit | 10 Pages | 20 Pages | 30 Pages
Image Optimization (Alt Text & Compression) | ✓ | ✓ | ✓
Internal Linking Strategy & Implementation | ✗ | ✓ | ✓
Performance Analytics & Strategic Review | ✓ | ✓ | ✓

## Pricing
$ 12000 - 3 months
Keyword Research & Mapping
40-60 Keywords target
monthly Google Analytics report (looker studios)
100 pages optimized
On-Page Optimization (Titles, Meta, Headers)
Technical SEO Audit (Crawlability, IndexNow, Speed, Core Web Vitals)
Ads Creation and launch
Content Creation & Optimization (Collection + Product Pages)
Content Gap Analysis & Content Plan for 6 Blogs
Weekly meeting

## gantt chart
TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | T | F | M | T | W | R | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Store Management: Low/Out-of-Stock Mgmt, Price & Sale Verification (promotions, discount codes), Homepage & Collection Updates (new products).
SEO Audit & Content: Full website SEO audit, Content Audits (Product, Collection, Pages), B2B keyword research, Content writing/updation. | bar: WEEK 1 M to WEEK 1 W; WEEK 5 M to WEEK 5 W; WEEK 9 W to WEEK 9 F
Optimization: Metadata writing/optimization for top 35 pages (Meta Title/Description/Keyword, H1/H2, Product description, FAQs, Images, Slug).
Technical SEO: Fixes for 35 identified pages (site speed, mobile, security, architecture, schema, duplicate content). | bar: WEEK 1 M to WEEK 1 W; WEEK 5 M to WEEK 5 W; WEEK 9 W to WEEK 9 F
Content: Create and Publish 2 blog posts. | bar: WEEK 2 M to WEEK 2 W; WEEK 4 M to WEEK 4 W; WEEK 6 M to WEEK 6 W; WEEK 8 M to WEEK 8 W; WEEK 10 M to WEEK 10 W; WEEK 12 M to WEEK 12 W
Google Ads Setup: Comprehensive audience | bar: WEEK 5 M to WEEK 5 W
Ads keyword research | bar: WEEK 5 T to WEEK 5 F
Campaign structure design (Shopping, Search, B2B) | bar: WEEK 6 M to WEEK 6 T
Merchant Center setup | bar: WEEK 6 W to WEEK 7 T
Ad copywriting | bar: WEEK 7 M to WEEK 7 W
Conversion tracking setup (GA4, GTM) | bar: WEEK 7 T to WEEK 7 F
Internal QA and bug fixing | bar: WEEK 8 M to WEEK 8 F
Ads Launch & Watch (tracking CPC, CTR, conversion data), Budget reallocation, Continuous optimization of keywords/bids/audiences, A/B testing (ad copy/creatives/LPs), Ads Scaling & SEO Expansion. | bar: WEEK 9 M to WEEK 12 F
Reporting: Generate report (Looker Studio / GA). | bar: WEEK 4 F; WEEK 8 F; WEEK 12 F
Weekly follow up | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F